## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Week 1 | Week 1 | US001 | Set up project infrastructure: JDK, IDE, Spring Boot, Maven/Gradle, database (MySQL/H2) | MUST HAVE | None | Sayyad Yasmin | 3- Completed
Week 1 | Week 2 | US002 | Train team on Java core features: Collections, Timers, JDBC | MUST HAVE | US001 | Sayyad Yasmin | 3- Completed
Week 2 | Week 2 | US003 | Define Task entity models with attributes (id, title, description, due date, status) | MUST HAVE | US001 | Sayyad Yasmin | 3- Completed
Week 3 | Week 3 | US004 | Implement Task Organization Engine: Add, update, list tasks using Java Collections | MUST HAVE | US003 | Sayyad Yasmin | 3- Completed
Week 3 | Week 3 | US005 | Connect Task Organization Engine to database via JDBC | MUST HAVE | US004 | Sayyad Yasmin | 3- Completed
Week 4 | Week 4 | US006 | Develop RESTful APIs for task operations (POST /tasks/add, GET /tasks/list, PUT /tasks/{id}) | MUST HAVE | US005 | Sayyad Yasmin | 3- Completed
Week 5 | Week 5 | US007 | Implement Scheduling System: Set timers for task due dates using ScheduledExecutorService | MUST HAVE | US006 | Sayyad Yasmin | 3- Completed
Week 5 | Week 5 | US008 | Integrate email API (JavaMail) to send reminders | MUST HAVE | US007 | Sayyad Yasmin | 3- Completed
Week 6 | Week 6 | US009 | Create Overview and CSV Integration Hub for task reports | SHOULD HAVE | US006 | Sayyad Yasmin | 2- In Progress
Week 6 | Week 6 | US010 | Develop Spring Boot APIs for scheduling and report generation (GET /reminders/{taskId}, GET /reports/overview, POST /reports/export) | MUST HAVE | US007, US009 | Sayyad Yasmin | 2- In Progress
Week 7 | Week 7 | US011 | Implement Completion Tracker to mark tasks as completed and track status | MUST HAVE | US006 | Sayyad Yasmin | 3- Completed
Week 7 | Week 7 | US012 | Develop APIs for completion tracking (PUT /completion/mark, GET /status/{taskId}) | MUST HAVE | US011 | Sayyad Yasmin | 2- In Progress
Week 8 | Week 8 | US013 | End-to-end testing of all modules with sample tasks | MUST HAVE | US006, US010, US012 | Sayyad Yasmin | 2- In Progress
Week 8 | Week 8 | US014 | Deploy full application and validate REST APIs | MUST HAVE | US013 | Sayyad Yasmin | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 76 | 7 | 20 | 23 | 14 | 6 | 5 | 1 | 13 | 5 | 5 | 1 | 6 | 6 | 1
SPRINT 1 BACKLOG
US001 | T001 | Install JDK & IDE | 2025-11-05 | 2025-11-05 | Yasmin | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US001 | T002 | Configure Spring Boot & Maven | 2025-11-07 | 2025-11-07 | Yasmin | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0
US002 | T003 | Database Setup (H2/MySQL) | 2025-11-10 | 2025-11-11 | Yasmin | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0
US002 | T004 | Define Task Entity Model | 2025-11-12 | 14-11-2025 | Yasmin | Design | 3- Completed | 3 | 0 | 5 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US003 | T005 | Learn Timers, JDBC, REST APIs | 15-11-2025 | 21-11-2025 | Yasmin | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US004 | T006 | Implement Task CRUD | 22-11-2025 | 24-11-2025 | Yasmin | Coding | 3- Completed | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US004 | T007 | Java Collections Integration | 25-11-2025 | 26-11-2025 | Yasmin | Coding | 3- Completed | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
US005 | T008 | JDBC Repository Integration | 26-11-2025 | 27-11-2025 | Yasmin | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US005 | T009 | REST APIs for Tasks | 27-11-2025 | 28-11-2025 | Yasmin | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US006 | T010 | Implement Scheduler using ScheduledExecutorService | 29-11-2025 | 2025-01-12 | Yasmin | Coding | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US006 | T011 | Implement Due Date Reminder Logic | 2025-02-12 | 2025-03-12 | Yasmin | Coding | 3- Completed | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US007 | T012 | Develop Reminder REST APIs | 2025-04-12 | 2025-05-12 | Yasmin | Coding | 3- Completed | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US008 | T013 | Generate Task Overview Report | 2025-06-12 | 2025-08-12 | Yasmin | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US008 | T014 | Implement CSV Export Feature | 2025-09-12 | 2025-10-12 | Yasmin | Coding | 3- Completed | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US009 | T015 | Develop Report Generation APIs | 2025-11-12 | 2025-12-12 | Yasmin | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US010 | T016 | Configure JavaMailSender | 13-12-2025 | 14-12-2025 | Yasmin | Build | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US010 | T017 | Develop Email Reminder Service | 15-12-2025 | 17-12-2025 | Yasmin | Coding | 3- Completed | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US011 | T018 | Unit Testing of Email Notifications | 18-12-2025 | 19-12-2025 | Yasmin | Unit Test | 3- Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US012 | T019 | Implement Task Completion Marking | 20-12-2025 | 22-12-2025 | Yasmin | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0
US012 | T020 | Develop Task Status REST APIs | 23-12-2025 | 24-12-2025 | Yasmin | Coding | 3- Completed | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0
US013 | T021 | Generate Pending vs Completed Reports | 25-12-2025 | 26-12-2025 | Yasmin | Others | 3- Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
US014 | T022 | Integrate Task, Scheduler & Completion Modules | 27-12-2025 | 29-12-2025 | Yasmin | Integration Test | 3- Completed | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1
US014 | T023 | End-to-End API Validation (Postman) | 30-12-2025 | 31-12-2025 | Yasmin | System Test | 3- Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US015 | T024 | Regression Testing After Fixes | 2026-01-01 | 2026-02-01 | Yasmin | Regression Test | 3- Completed | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US016 | T025 | Fix Remaining Bugs & Code Cleanup | 2026-01-03 | 2026-05-01 | Yasmin | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0
US016 | T026 | Deploy Application & Verify APIs | 2026-01-04 | 2026-07-01 | Yasmin | Build | 3- Completed | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
US017 | T027 | Prepare Final Documentation & Submission | 2026-01-08 | 2026-01-09 | Yasmin | Others | 3- Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Week 1 | Day 1 | Unable to set up database connection | Configured correct JDBC URL and verified driver installation
Week 1 | Day 6 | Spring Boot dependencies failed to load | Updated Maven dependencies and re-imported project
Week 2 | Day 9 | Confusion on Java Collections usage for tasks | Referred to Java docs and implemented ArrayList/HashMap structure
Week 3 | Day 20 | Task REST API not returning data | Debugged controller and repository methods; fixed mapping issue
Week 4 | Day 25 | Timer for reminders not triggering | Tested ScheduledExecutorService with sample tasks; corrected cron expressions
Week 5 | Day 33 | Email API (JavaMail) authentication errors | Enabled less-secure app access in email settings and added proper credentials
Week 6 | Day 45 | CSV export formatting issues | Adjusted CSV writer logic to include headers and proper delimiters
Week 7 | Day 47 | Completion tracker not updating status in DB | Verified JDBC update queries and added transaction handling
Week 8 | Day 53 | API deployment failed on server | Checked server logs, updated application.properties, redeployed application

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 15-11-2025 | 21-11-2025 | Yasmin | Plan project structure and setup Spring Boot | Guessing DB configs | Setting up project with correct packages | Installed JDK, Spring Boot, Maven, H2 DB, created task model
2 | Sprint 2 | 22-11-2025 | 28-11-2025 | Yasmin | Write APIs after planning | Hardcoding collections | Using Postman to test APIs | Implemented Task Organization Engine: add/list/update tasks, tested APIs
3 | Sprint 3 | 29-11-2025 | 2025-05-12 | Yasmin | Start implementing timers & scheduling early | Ignoring edge cases in due dates | Using ScheduledExecutorService for tasks | Added scheduler system, timer logic for due dates, tested reminders
4 | Sprint 4 | 2025-06-12 | 2025-12-12 | Yasmin | Early CSV export and reporting | Skipping CSV validations | Continue using OpenCSV for reports | Implemented CSV export and overview APIs, tested via Postman
5 | Sprint 5 | 13-12-2025 | 19-12-2025 | Yasmin | Start email reminders integration | Delaying email integration | Continue testing each feature incrementally | Configured JavaMailSender, EmailUtil, and tested scheduled email reminders
6 | Sprint 6 | 20-12-2025 | 26-12-2025 | Yasmin | Start completion tracker and status updates | Skipping status updates | Continue using Postman for debugging | Added completion tracker API, status updates, tested pending/completed tasks
7 | Sprint 7 | 27-12-2025 | 2026-02-01 | Yasmin | Combine frontend & backend testing | Manual testing without HTML | Continue documenting & testing | Connected frontend HTML with backend APIs, tested all buttons, CSV export, overview, scheduling
8 | Sprint 8 | 2026-03-01 | 2026-09-01 | Yasmin | Final bug fixes & project polishing | Ignoring minor bugs | Continue testing all workflows | Fixed remaining bugs, verified API + frontend integration, prepared final submission